## Vendor Details
VENDOR DETAILS
Vendor | Risk Tier | Business Criticality | Service Type
PaySure Ltd. | Medium | High | Payroll & employee data processing
SyncCloud Inc. | High | Critical | Cloud infrastructure (IaaS)
AdzPulse Co. | Low | Low | Marketing analytics SaaS
DocuVault | Medium | Medium | Document management + e-signature
TrustID | High | High | Identity verification & authentication
NexusCore | Low | Low | IT hardware procurement
MediPortRx | Medium | High | Claims processing & health data
TransFleet | Low | Medium | Logistics/transportation service
RegiComply | High | Critical | Regulatory compliance SaaS platform
FinSight AI | Medium | Medium | Predictive financial analytics tool

## KRI Mapping & Escalation Matrix
KRI MAPPING BY RISK TIER
Key Risk Indicators (KRI) | High Tier Vendors | Medium Tier Vendors | Low Tier Vendors | Severity | Why
Outstanding Risk Remediation (Age > 60 Days) | Required | Required | Optional (review bi-annually) | Moderate | Signals delay in closing known risks; time-sensitive, but expected in some cases
Policy/Cert Expiry (e.g., SOC, ISO) | Required | Required | Required | Moderate | A lapse weakens trust/compliance but often manageable with tracking
SLA/Uptime Breach | Required | Required | Optional (only if SLAs are in place) | Moderate | Impacts operational reliability; severity depends on frequency
Negative OSINT or Security Event | Required | Required | Required | Critical | Real-time risk, reputational exposure, possible regulatory consequence
Overdue Questionnaire / Risk Response | Required | Required | Not required | Moderate | Indicates poor engagement or early signs of misalignment
Personnel Offboarding Lag | Required | Optional (only if access to systems) | Not required | Critical | Direct access control failure; high likelihood and potential for breach
Major Change in Service or Subcontractor Use | Required | Required | Not required | Moderate | Can bypass contract controls; needs timely attention
Unreviewed Contract for >24 Months | Required | Optional (bi-annually) | Not required | Low | More strategic than urgent; often flagged in annual planning
TPRM Escalation Matrix (Severity-Based Triggers)
Risk Tier | KRI Severity Triggered | Escalation Action | Timeframe | Stakeholders Notified
High | 1+ Critical KRI | Immediate vendor contact, remediation required, log in issue tracker | Within 1–2 business days | GRC, Security, Legal, Business Owner
| 2+ Moderate KRIs | Require remediation plan; escalate in risk governance forums | Within 3–5 business days | GRC, Procurement, Business Owner
| 2+ Low KRIs (no moderate/critical) | Flag for tracking; no immediate action | Monthly review | GRC
Medium | 1 Critical KRI | Require documented response and executive sign-off for continued engagement | Within 3 business days | GRC, Legal, Procurement
| 2+ Moderate KRIs | Require remediation plan; escalate if not resolved by next review cycle | Within 5–7 business days | GRC, Business Owner
| 2+ Low KRIs | Log for next periodic review and trend analysis | Quarterly | GRC
Low | 1 Critical KRI | Immediate reassessment or pause engagement; consider temporary elevation to Medium risk tier | Within 3-5 business days | GRC, Security, Procurement
| 3+ Moderate KRIs | Contact vendor for explanation; flag for contract review or reassessment | Within 7–10 business days | GRC only
| 3+ Low KRIs | Add to watchlist; review at next scheduled vendor check-in | Bi-annually | GRC

## KRI Monitoring Log
KRI Monitoring Log
Date Logged | Vendor Name | Risk Tier | Business Criticality | KRI Triggered | Severity | Details / Evidence | Status | Escalation Required? | Next Action / Owner
2024-04-01 | PaySure Ltd. | Medium | High | Policy/Cert Expired (SOC2) | Moderate | Cert expired Mar 20; new audit delayed | Open | No | Follow up with vendor – GRC
2024-04-03 | SyncCloud Inc. | High | Critical | Personnel Offboarding Delay | Critical | User had access for 9 days post-termination | Escalated | Yes | Notify Security & Risk Committee
2024-04-05 | AdzPulse Co. | Low | Low | No active KRIs | — | N/A | N/A | No | Next review: Q3 – GRC
2024-04-06 | TrustID | High | High | Negative OSINT: Potential data leak | Critical | Mentioned in breach intel report (March incident) | Escalated | Yes | Risk review underway – GRC + Legal
2024-04-08 | DocuVault | Medium | Medium | Overdue Security Questionnaire | Moderate | 40+ days overdue | Open | No - Monitor only | Reminder email sent – Procurement
2024-04-16 | RegiComply | High | Critical | Personnel Offboarding Lag (7 days) | Critical | Access terminated 7 days after departure, logs confirm delay | Escalated | Yes | Require access audit + remediation
2024-04-17 | NexusCore | Low | Low | None | — | No KRIs identified during this cycle | N/A | No | Monitor during next semiannual review
2024-04-18 | MediPortRx | Medium | High | Security questionnaire overdue (45+ days) | Moderate | Repeated delays in questionnaire return for 2nd cycle | Open | Yes – escalate if unresolved | Follow-up email + remediation timeline – GRC
2024-04-18 | TransFleet | Low | Medium | MFA misconfiguration (no enforcement for admins) | Moderate | Audit report shows MFA not enforced for 3 privileged accounts | Open | No – monitor only | Add to next scheduled vendor review – GRC
2024-04-18 | FinSight AI | Medium | Medium | Data access logs missing for 2 weeks | Critical | SOC findings showed missing logs for privileged database access | Escalated | Yes - immediate | Initiate remediation plan + report to GRC/Legal